Database Flexibility in Frappe

Feasibility & Implementation Mechanism

ClickUp task: Database flexibility in Frappe (86d46ay07)

Driver: Client requirement (PLM) — build deferred, feasibility required now

Date: September 2, 2026

Deliverable: Proven routing mechanism + reference adapter

# 1. Where Frappe Already Is

Frappe's storage layer is more pluggable than it first appears. Four adapters ship today — MariaDB, Postgres, SQLite and DuckDB — all implementing one Database base class contract covering reads, writes, counts, escaping and transactions. That contract is the specification any new backend has to satisfy; it does not have to be invented.

Two caveats found in the code. Backend selection is dispatched through scattered conditionals on the configured database type rather than a registry, so adding a backend today means finding every branch — worth fixing first regardless of direction. And four subsystems assume a single SQL database more deeply than plain reads and writes do: permission enforcement (which injects SQL conditions), user-authored SQL reports, the cross-DocType search index, and schema migration. Those four are the real cost of this work, not create/read/update/delete.

# 2. The Mechanism

Frappe exposes a controller override hook that lets a separate app supply its own controller class for a specific DocType, intercepting the persistence methods. That is the whole basis of the approach, and it is what keeps this out of a framework fork: core is untouched, so upstream releases keep merging cleanly.

Per-DocType routing. A registry maps DocType to backend, read from site configuration rather than hardcoded. Any DocType not in the registry uses the default relational path unchanged — which will be the overwhelming majority, and is why the blast radius stays small.

The adapter contract. Each backend implements the same narrow interface — insert, load, update, delete, list-with-filters, count — modelled on the existing Database base class. A backend that cannot honour an operation says so explicitly instead of failing quietly (§8).

Cross-store references. This is the hard part and the part the requirement actually turns on. When a relationally-stored DocType links to one stored elsewhere, the join cannot happen inside a single query. It is resolved above the storage layer: fetch identifiers on one side, fetch records on the other, assemble the result so the caller sees one coherent document. Callers do not know a boundary was crossed.

Consistency. Writes spanning two stores are not atomic and cannot be made so by wrapping them in optimism. The relational row is the existence record, written first; the secondary store is written second; a reconciliation job repairs partial failures. This is a property of the design, not a defect to be hidden — and it needs the client's explicit sign-off, because 'behaves as one database' cannot mean full ACID across two engines.

Feature boundaries. User-authored SQL reports cannot run against a non-SQL-backed DocType. The correct behaviour is an explicit, clearly-worded limitation surfaced in the interface, never a silent empty result (§8). Permission filtering and search indexing each need a purpose-built implementation for such a DocType.

# 3. Options

| Option | Approach | Pros | Cons |
| --- | --- | --- | --- |
| A — JSON column in the existing store | Variable attributes held in a JSON/JSONB column on the existing table. | No cross-store problem at all. Comfortably handles the write volumes discussed (thousands per minute) at ordinary document sizes. | Delivers schema flexibility, not a different engine. Costly only with large documents at very high write rates. |
| B — Per-DocType polyglot persistence | Specific DocTypes routed to specific engines through controller overrides, with cross-store reference resolution. | Delivers the literal requirement; each DocType can sit on the engine that suits its access pattern. | Router, adapter, resolver and reconciliation to build and maintain; several framework features need bespoke handling per routed DocType. |
| C — Fully swappable core | Every DocType portable to any engine with full feature parity. | Satisfies the most expansive reading of the requirement. | An open-ended rewrite of the model and query layers, permanently diverging from upstream. Not recommended. |

Recommendation: establish which specific data actually needs non-relational storage, and why, before building Option B. If the underlying need is schema flexibility at moderate write volume, Option A delivers it at a fraction of the cost — and that determination is a conversation, not a spike. If the need is a genuinely different access pattern, scope Option B to that data rather than to 'any DocType, any store'.

# 4. Plan

This runs alongside the Clockapp build week rather than blocking it, and produces a reference implementation the wider team can extend later.

| ID | Task | Owner | Est | Depends on |
| --- | --- | --- | --- | --- |
| D1 | Replace scattered backend dispatch with a registry | Arch | 0.5 | — |
| D2 | Formalise the adapter contract from the existing base class | Arch | 0.5 | D1 |
| D3 | Reference adapter for one non-relational engine: create, read, update, delete, list | Arch | 1.5 | D2 |
| D4 | Cross-store reference resolution for reads and filtered lists | Arch | 1.5 | D3 |
| D5 | Consistency strategy: write ordering plus reconciliation job | Arch | 1 | D4 |
| D6 | Boundary handling: permissions, search indexing, explicit report limitation | Team | 1.5 | D4 |
| D7 | Migration mechanism for the routed backend | Team | 1 | D3 |
| D8 | Tests: correctness, cross-store joins, failure-mode consistency, permissions | Team | 1.5 | D5 |
| D9 | Developer guide: how to route a DocType to another backend | Arch | 0.5 | D6 |

Sequence: D1–D5 (architecture, Sep 7–11) prove the mechanism end to end on one DocType. D6–D9 follow once the client has named the data this is for; without that, everything past D5 is building for a hypothesis.

# 5. Feasibility Summary

Mechanically, this is feasible and the framework cooperates with it: the adapter contract exists, the controller override hook exists, and no fork is required. The genuine costs are cross-store reference resolution, the loss of atomic writes across engines, and per-DocType reimplementation of permission filtering and search for anything routed off the relational store. Those are all bounded and known — they are only unbounded if the goal is stated as 'any DocType on any engine with full feature parity', which is the option this document recommends against.

Database flexibility — feasibility and mechanism